Sean Davis

Delta Innovations | Orlando, FL

System Hardening

Sean Davis

Orlando, FL

Table of Contents

Project Overview	2

Project Goals & Objectives (Benefits)	2

Network Infrastructure Requirement	3

Assumptions & Risks	3

Work Breakdown Structure (WBS)	3

Network Topology Diagram with IP Addresses	4

Appendices	4

DISA STIGs	4

# Scope of Work

Project Title

System Hardening

# Project Overview

Marconi Law is looking to upgrade from a locally managed web server to the cloud in a two-step process with an emphasis on security.  Project System Hardening aims to design an end-to-end automated deployment of two (2) web servers on the Digital Ocean cloud platform using Ansible software. Ansible is an open-source IT automation tool known to be the best in the market today. It frees IT administrators up to focus on efforts that help deliver more value to the business by speeding time to application delivery.

  First, a single automated script will be developed/coded to provision two (2) Digital Ocean Droplets (instances) and deploy Defense Information Systems Agency (DISA) Security Technical Implementation Guidelines (STIGs), a collection of known security fixes, onto them.

  Second, several test and validation processes will be conducted to ensure, 1) the stability and consistency of the script, and 2) the outcome of the end-to-end automated deployment of 2 security hardened web servers is identical every time.

The final delivery date for the project is June 5, 2019. Milestone completion dates are as follow:

Milestone completion dates:

Milestone I – May 9, 2019

Milestone II – May 13, 2019

Milestone III – May 17, 2019

Milestone IV – May 22, 2019

Milestone V – May 24, 2019

Milestone VI – May 28, 2019

Milestone VII – May 30, 2019

Milestone VIII – June 5, 2019

# Project Goals & Objectives (Benefits)

- Security - The systems are designed from the ground up for security with controls aimed at minimizing both physical and logical risks

- Speed - The web servers will be equipped to be responsive at all hours of the day. Performance can be scaled to meet growing needs of the company.

- Reliability - By utilizing the Digital Ocean cloud platform by SLA the systems will have a 100% network and 99.99% droplet uptime. SLA also includes 24/7 support 365 days a year.

- Scalability - The system must be scalable to fit the needs of the company within a short window. Not only can more be provisioned but existing ones can have their CPU, RAM, and storage increased as needed.

# Network Infrastructure Requirement

1 Virtual Machine

OS: Centos 7.4

Applications: Ansible 2.7.6, dopy

Memory: 1GB

Hard Drive: 20GB

2 Digital Ocean Droplets

OS: Centos 7.0

Applications: Apache, MariaDB, PHP

Memory: 512MB

HD: 20GB

# Assumptions & Risks

- Marconi Law must provide a Digital Ocean account as well as be aware of all terms and conditions of the Digital Ocean service level agreement (SLA) and billing policies. The final product will be subject to these terms.

- Internet Access is required during the provisioning and management processes.

- Delta Innovations will provide the infrastructure only, anything beyond that including the web servers intended functions, design, domain name acquisition, and configuration is the responsibility of Marconi Law

- System Security is a never-ending process the scope of this project is limited to the hardening processes listed in this document. Marconi Law must keep up with the security community or enlist a security contractor to ensure continuity.

- Delta Innovations is not liable nor provides breach/cyber insurance in the event of a security incident.

# Work Breakdown Structure (WBS)

- System Hardening

  - Research

    - Digital Ocean

    - Digital Ocean Ansible Connectivity

    - Ansible Instance Provisioning

    - Centos DISA STIGS

    - Ansible DISA STIG deployment

  - Digital Ocean Account Foundation

    - Account Creation

    - API Key Generation

  - Ansible Machine

    - Set up Virtual Machine

    - Install Operating System

    - Install Ansible

    - Interface Ansible with Digital Ocean

  - Provisioning Portion of Script

    - SSH Keygen & Upload

    - Droplet Provision

    - Host File Update

  - Lamp Portion of Script

    - Packages

    - Firewall Ports

  - STIG Deployment Portion of Script

    - Cat 1 High Risk STIG

    - Cat 2 Moderate Risk STIG

  - Testing

    - Code Quality Assurance

    - Dry Run

    - Security Inspection

  - Deliverable Presentation and Training

    - Final Deliverable Presentation

    - Integration and Customer Training

Closeout Paperwork.

# Network Topology Diagram with IP Addresses

# Appendices

## DISA STIGs

List all of the STIGs used in this project and provide a summary description for each.

| Stig # | Risk Category | Description |
| --- | --- | --- |
| RHEL-07-010020 | (Cat 1) High | cryptographic hash of system files and commands matches vendor values |
| RHEL-07-010020 | (Cat 1) High | Reinstallation of packages necessary for above audit |
| RHEL-07-010300 | (Cat 1) High | Linux operating system must be configured so that the SSH daemon does not allow authentication using an empty password |
| RHEL-07-010290 | (Cat 1) High | Linux operating system must not have accounts configured with blank or null passwords |
| RHEL-07-020000 | (Cat 1) High | Linux operating system must not have the rsh-server package installed |
| RHEL-07-020010 | (Cat 1) High | Linux operating system must not have the ypserv package installed |
| RHEL-07-020050 | (Cat 1) High | Package handler will only install packages from a certified digitally signed repository entry |
| RHEL-07-020220 | (Cat 1) High | Linux operating system must enable the SELinux targeted policy. |
| RHEL-07-020230 | (Cat 1) High | Linux operating system must be configured so that the x86 Ctrl-Alt-Delete key sequence is disabled |
| RHEL-07-020310 | (Cat 1) High | Linux operating system must be configured so that the root account must be the only account having unrestricted access to the system |
| RHEL-07-021350 | (Cat 1) High | Linux operating system must implement NIST FIPS-validated cryptography |
| RHEL-07-021710 | (Cat 1) High | Linux operating system must not have the telnet-server package installed |
| RHEL-07-030000 | (Cat 1) High | Linux operating system must be configured so that auditing is configured to produce records containing information to establish what type of events occurred |
| RHEL-07-040390 | (Cat 1) High | SSH daemon is configured to only use the SSHv2 protocol." |
| RHEL-07-040690 | (Cat 1) High | File Transfer Protocol (FTP) server package uninstalled |
| RHEL-07-040700 | (Cat 1) High | Trivial File Transfer Protocol (TFTP) server package uninstalled |
| RHEL-07-040710 | (Cat 1) High | Mandates that remote X connections for interactive users are encrypted |
| RHEL-07-040800 | (Cat 1) High | SNMP Community String changed from default |
| RHEL-07-010119 | (Cat 2) Moderate | Ensures when passwords are changed or new passwords are established, pwquality must be used |
| RHEL-07-010200 | (Cat 2) Moderate | PAM system service is configured to store only encrypted representations of passwords |
| RHEL-07-010220 | (Cat 2) Moderate | User and group account administration utilities are configured to store only encrypted representations of passwords |
| RHEL-07-010270 | (Cat 2) Moderate | Passwords are prohibited from reuse for a minimum of five generations |
| RHEL-07-010310 | (Cat 2) Moderate | Disables account identifiers (individuals, groups, roles, and devices) if the password expires |
| RHEL-07-010460 | (Cat 2) Moderate | Linux operating system must not allow users to override SSH environment variables |
| RHEL-07-010470 | (Cat 2) Moderate | Linux operating system must not allow a non-certificate trusted host SSH logon to the system |